

**Program Review Leadership Development**

**ORIENTATION**

**TO**

**PROGRAM REVIEW**

**MAY 2013**

 

2013-2014 Program Review Process

Spring Implementation

**Timeline**

12 months from start of training and data collection to final report

**12 Month Human Resource Commitment *per Program***

Program Quality and Curriculum Design: TBD

Institutional Research: TBD

Program Review Academic Lead: approximately 80 hours

Individual Program Faculty: approximately 30 hours each

**Data Collection: 12 Month Human Resource Commitment *per Program***

Program Quality and Curriculum Design: TBD

Institutional Research: TBD

Program Review Academic Lead: approximately 40 hours (including 18 training hours and monthly 2 hour meetings)

Individual Program Faculty: approximately 18 hours

**Data Analysis: 12 Month Human Resource Commitment *per Program***

|  |  |
| --- | --- |
| Program Quality and Curriculum Design | 8 hours per program |
| Institutional Research | 4 hours per program |
| Program Review Academic Lead | Approximately 36 hours = 3 hours for each Curriculum, Market Demand, Program Quality Analysis sessions and 20 hours to write the draft final report |
| Individual Program Faculty | Approximately 12 hours |

|  |
| --- |
| ***PROPOSED* TRAINING SCHEDULE: PROGRAM REVIEW LEADERSHIP DEVELOPMENT****PROGRAM REVIEWS, STARTING SPRING 2013** |
| **SESSION** | **DATE** | **TOPIC** | **PARTICIPANTS** |
| 1 | May 7 | Overview of Program Review Process and Program Review Leadership Development Program | Associate Deans, Program Review Leads, Program Quality and Institutional Research Team |
|  |  |  |  |
| 2 | May 14 | Keeping the End in Mind: Sample Program Review ReportDetermine Timelines: Up-Front Checklist | Program Review Leads, Curriculum Design Specialists  |
|  |  |  |  |
| 3 | May 21 | Program Quality: Data Collection | Program Review Leads, Curriculum Design Specialists |
|  |  |  |  |
| 4 | May 28 | Program Quality: Data Collection (cont’d)  | Program Review Leads, Curriculum Design Specialists  |
|  |  |  |  |
| 5 | June 4 | Piquing Your Interest: Sample Environmental Scan | Program Review Leads, Curriculum Design Specialists, Research Analyst  |
|  |  |  |  |
| June 11No Scheduled Session |
| 6 | June 18 | Aligning Program Quality to Strategic and Academic Plans | Program Review Leads, Curriculum Design Specialists, PLAR and Pathways Representative |
|  |  |  |  |
| On-going Support | Fall / Winter | Monthly Meetings (TBD): Curriculum Design Specialists and PRLD Leads | Program Review Leads, Curriculum Design Specialists |

| **Program Review****Detailed Workplan** |
| --- |
| **PURPOSE OF ACTIVITY** | **TOPIC** | **SUB-TOPICS** | **PRIMARY RESPONSIBILITY FOR IMPLEMENTATION** | **TOOLKIT #** | **DUE DATES****Organize Dates****Self-Directed****Someone Else Does the Work** | **STATUS OF WORK****(✓ if complete)** |
| **DATA COLLECTION** | **PROGRAM QUALITY: CURRICULUM** | Course Outlines  | * Program Review Lead
* Curriculum Design
 | 1a |  |  |
| * Option A: Full course outline review, including revisions
 | Workshops: Oct. 21, 2013 (9am-12pm)Or Feb. 24, 2014 (9am-12pm) |  |
| * Option B: Report status of program course outlines and plan for review in Action Plan
 | Option B: Dec. 21, 2013 |  |
| Mapping to Vocational Standards, Essential Employability Skills | * Program Review Lead
* Faculty
 | 1b | Workshops:Oct. 21, 2013(1pm-4pm)OrOct. 22, 2013(9am-12pm) |  |
| Strategic Curriculum Discussion | * Program Review Lead
 | 3 | Jan. 30, 2014 |  |
| Credentials Framework | * Program Review Lead
 | 6 | Feb. 28, 2014 |  |
| Program Advisory Committee Assessment | * Program Review Lead
 | 8 | Dec. 21, 2013 |  |
| Competitive Curriculum Analysis | * Program Quality
* Institutional Research
 | 9 | Sept, 1, 2013 |  |
| **PROGRAM QUALITY: PATHWAYS** | Pathways, Partnerships and Articulations | * Program Review Lead
 | 5 | Feb. 28, 2014 |  |
| **PROGRAM QUALITY: PROGRAM INFORMATION** | POS Change Report | * Program Quality
 | 9 | Sept. 1, 2013 |  |
| Program System Matrix | * Program Review Lead
 | 7 | Dec. 21, 2013 |  |
| **PROGRAM QUALITY: ALIGNMENT WITH ACADEMIC PLAN** | Aligning Assessment with Outcomes and Program Level Assessment Mapping  | * Program Review Lead
 | 4 | Workshops:Oct. 22, 2013 (1pm-4pm)OrFeb. 25, 2014 (1pm-4pm) |  |
| Program Delivery | * Program Quality
* Institutional Research
 | 9 | Dec. 21, 2013 |  |
| Other - TBD | * Program Quality
 | TBD | TBD |  |
| **MARKET DEMAND: ENVIRONMENTAL SCAN** | * Competitive Program Profile
* KPI
* Program Scorecard
* Student Success and Retention
* Student Migration and Tracking
* Employment Demand
* Labour Market Demand
 | * Institutional Research Analyst
 | 2 | All Data will be available on Sept. 1, 2013 |  |
| **DATA ANALYSIS** | **PROGRAM QUALITY ANALYSIS SESSIONS** | Analysis of:* Curriculum Mapping Matrix
* Competitive Curriculum Report
* Results of Strategic Curriculum Discussion
* Credentials Framework
* PAC
* POS Change Report
* Program System Matrix
* Program Delivery
 | * Associate Dean
* Program Review Lead
* Faculty
* Curriculum Design Specialist
 | 9 | Two 3-hour meetings between Jan. 1, 2014 and Feb. 28, 2014 |  |
| **MARKET DEMAND: ENVIRONMENTAL SCAN** | * Competitive Program Profile
* KPI
* Program Scorecard
* Student Success and Retention
* Student Migration and Tracking
* Employment Demand
* Labour Market Demand
 | * Associate Dean
* Institutional Research Analyst
* Program Review Lead
* Faculty
* Curriculum Design Specialist
 | 2 | One 3-hour meetingbetween Sept. 1, 2013 to Feb. 1, 2014 |  |
| **DRAFT OF FINAL REPORT** | Validation of and agreement on contents of final report …* Observations
* Recommendations
* Action plans
 | * Associate Dean
* Institutional Research Analyst
* Program Review Lead
* Faculty
* Curriculum Design Specialist
 | 10 | One 3-hour meeting between Feb. 28, 2014 and March 18, 2014 |  |
| **FINAL REPORT** | **DRAFT OF FINAL REPORT** | To Curriculum Design Specialist for review | * Curriculum Design Specialist
 | 10 | March 19, 2014 |  |
| To Associate Dean for review and approval | * Program Review Lead
 | March 26, 2014 |  |
| To Dean for review and approval | * Associate Dean
 | April 9, 2014 |  |
| **FINAL REPORT** | To Vice President Academic (via Program Quality Project/Process Consultant, Roberta Weiss) | * Dean
 | 10 | April 30, 2014 |  |